## pacman 24
PacMan 24 |  | This spreadsheet was created using monday.com
Group Title |  | Try it free →
Name | Subitems | People | Timeline | Duration | Dependency | Status
Project planning and requirements analysis |  | Alexander Bachuirin | 2026-05-11 - 2026-05-13 | 3
Research original Pac-Man mechanics |  | Alexander Bachuirin, Irek Iunusov | 2026-05-14 - 2026-05-20 | 7 | Project planning and requirements analysis
Design software architecture |  | Alexander Bachuirin, Irek Iunusov | 2026-05-21 - 2026-05-25 | 5 | Research original Pac-Man mechanics
Set up Python/Pygame development environment |  | Irek Iunusov | 2026-05-21 - 2026-05-21 | 1 | Research original Pac-Man mechanics, Project planning and requirements analysis
Modules Development | Artifacts, Config class, Application class, Game class, Player - PacMan, Screens, Ghosts, Maze class | Alexander Bachuirin, Irek Iunusov | 2026-05-26 - 2026-06-20 | 37 | Design software architecture, Set up Python/Pygame development environment
Config class | Parsing - read from json (with Pydantic), Parameters structure, Parsing without Pydantic for web | Irek Iunusov | 2026-05-26 - 2026-05-28 | 3 | Design software architecture
Parameters structure |  | Irek Iunusov | 2026-05-26 - 2026-05-26 | 1 | Design software architecture, Set up Python/Pygame development environment
Parsing - read from json (with Pydantic) |  | Irek Iunusov | 2026-05-27 - 2026-05-27 | 1 | Parameters structure
Parsing without Pydantic for web |  | Irek Iunusov | 2026-05-28 - 2026-05-28 | 1 | Parsing - read from json (with Pydantic), Parameters structure
Maze class | Rendering - Draw maze, Path finding in maze, Read maze from file, Using external library to generate maze, Delete dead ends in the maze | Alexander Bachuirin | 2026-05-29 - 2026-06-02 | 5 | Config class
Using external library to generate maze |  | Alexander Bachuirin | 2026-05-29 - 2026-05-29 | 1 | Parsing - read from json (with Pydantic)
Read maze from file |  | Alexander Bachuirin | 2026-05-30 - 2026-05-30 | 1 | Using external library to generate maze
Rendering - Draw maze |  | Alexander Bachuirin | 2026-05-31 - 2026-05-31 | 1 | Read maze from file
Path finding in maze |  | Alexander Bachuirin | 2026-06-01 - 2026-06-01 | 1 | Rendering - Draw maze
Delete dead ends in the maze |  | Alexander Bachuirin | 2026-06-02 - 2026-06-02 | 1 | Path finding in maze
Application class | Full screen mode, Screen size management, Screen switch | Irek Iunusov, Alexander Bachuirin | 2026-06-03 - 2026-06-05 | 3
Screen switch |  | Irek Iunusov | 2026-06-03 - 2026-06-03 | 1 | Maze class
Screen size management |  | Alexander Bachuirin | 2026-06-04 - 2026-06-04 | 1 | Screen switch
Full screen mode |  | Alexander Bachuirin | 2026-06-05 - 2026-06-05 | 1 | Screen size management
Game class | New game init, Game main circle, New level | Alexander Bachuirin | 2026-06-06 - 2026-06-08 | 3
New game init |  | Alexander Bachuirin | 2026-06-06 - 2026-06-06 | 1 | Application class
New level |  | Alexander Bachuirin | 2026-06-07 - 2026-06-07 | 1 | New game init
Game main circle |  | Alexander Bachuirin | 2026-06-08 - 2026-06-08 | 1 | New level, New game init
Screens | Error screen, Game end screen, Instruction screen, Main menu screen, High scores screen, Base class for screen | Irek Iunusov | 2026-06-06 - 2026-06-09 | 6
Base class for screen |  | Irek Iunusov | 2026-06-06 - 2026-06-06 | 1 | Application class
Main menu screen |  | Irek Iunusov | 2026-06-07 - 2026-06-07 | 1 | Base class for screen
Instruction screen |  | Irek Iunusov | 2026-06-08 - 2026-06-08 | 1 | Main menu screen
Error screen |  | Irek Iunusov | 2026-06-08 - 2026-06-08 | 1 | Main menu screen
Game end screen |  | Irek Iunusov | 2026-06-08 - 2026-06-08 | 1 | Main menu screen
High scores screen |  | Irek Iunusov | 2026-06-09 - 2026-06-09 | 1 | Game end screen, Main menu screen
Player - PacMan | Movement and collision detection, Base class (Entity), Rendering and animation | Alexander Bachuirin | 2026-06-09 - 2026-06-13 | 5
Base class (Entity) |  | Alexander Bachuirin | 2026-06-09 - 2026-06-09 | 1 | Game main circle
Rendering and animation |  | Alexander Bachuirin | 2026-06-10 - 2026-06-10 | 1 | Base class (Entity)
Movement and collision detection |  | Alexander Bachuirin | 2026-06-11 - 2026-06-13 | 3 | Rendering and animation
Ghosts | Frightened mode, AI - Chase algorithm, Base class (NPC), Events - collision with PacMan, Rendering - Animation | Alexander Bachuirin, Irek Iunusov | 2026-06-09 - 2026-06-16 | 8
Base class (NPC) |  | Irek Iunusov | 2026-06-09 - 2026-06-09 | 1 | Maze class, Game class
Rendering - Animation |  | Alexander Bachuirin | 2026-06-10 - 2026-06-10 | 1 | Base class (NPC)
Events - collision with PacMan |  | Alexander Bachuirin | 2026-06-11 - 2026-06-11 | 1 | Rendering - Animation
AI - Chase algorithm |  | Irek Iunusov | 2026-06-12 - 2026-06-15 | 4 | Events - collision with PacMan
Frightened mode |  | Irek Iunusov | 2026-06-16 - 2026-06-16 | 1 | AI - Chase algorithm
Artifacts | Rendering, Event, PowerPellet, BonusFruit | Alexander Bachuirin | 2026-06-17 - 2026-06-20 | 4 | Ghosts
Rendering |  |  | 2026-06-17 - 2026-06-17 | 1
Event |  |  | 2026-06-18 - 2026-06-18 | 1
PowerPellet |  |  | 2026-06-19 - 2026-06-19 | 1
BonusFruit |  |  | 2026-06-20 - 2026-06-20 | 1
Images - Create images for animation | Ghost, Fruits, PacMan | Alexander Bachuirin | 2026-06-03 - 2026-06-08 | 6 | Maze class
PacMan |  | Alexander Bachuirin | 2026-06-03 - 2026-06-04 | 2
Ghost |  | Alexander Bachuirin | 2026-06-05 - 2026-06-06 | 2 | PacMan
Fruits |  | Alexander Bachuirin | 2026-06-07 - 2026-06-08 | 2 | Ghost
Sound - Record and prepare |  | Alexander Bachuirin | 2026-06-09 - 2026-06-12 | 4 | Images - Create images for animation
Testing and bug fixing | User Acceptance Testing (UAT), Test plan developing, Integration Testing | Alexander Bachuirin, Irek Iunusov | 2026-06-21 - 2026-07-02 | 12
Test plan developing |  |  | 2026-06-21 - 2026-06-22 | 2 | Modules Development
Integration Testing |  |  | 2026-06-23 - 2026-06-27 | 5 | Test plan developing
User Acceptance Testing (UAT) |  |  | 2026-06-28 - 2026-07-02 | 5 | Integration Testing
Prepare executable/web build | linux, windows, web | Irek Iunusov, Alexander Bachuirin | 2026-07-03 - 2026-07-07 | 6
web |  | Alexander Bachuirin | 2026-07-03 - 2026-07-06 | 4 | Testing and bug fixing
windows |  | Alexander Bachuirin | 2026-07-07 - 2026-07-07 | 1 | web
linux |  | Irek Iunusov | 2026-07-07 - 2026-07-07 | 1 | web
Write project documentation |  |  | 2026-07-03 - 2026-07-07 | 5 | Testing and bug fixing
Deployment (Itch.io) |  | Irek Iunusov | 2026-07-08 - 2026-07-09 | 2 | Prepare executable/web build, Testing and bug fixing, Write project documentation
|  |  | 2026-05-11 - 2026-07-09 | 88